## Comp Plan - Simple
EPM Name | Jane Smith |  |  | EPM Commencement Date | 2023-07-01 | Date updated | 2023-07-01
EPM Title | Facilities Engineer |  |  | Energy Cost ($/kWh) | 0.07
Site Name | Acme Incorporated |  |  | Baseline Usage (kWh/yr) | 25000000 | BEETS App ID | VYPMCR1550500959
Acme Incorporated Energy Project Manager Comprehensive Plan
Project Planning and Tracking | [7 empty] | Project Completion Information
Project Description | Project Type | Project Status | Est. Project Cost ($) | Est. Savings (kWh/yr) | Est. Completion Date | Brief Description of Savings Approach | Notes | Completion Date | Verified Site Savings (kWh/yr) | Verified Busbar Savings (kWh/yr) | BEETS Application ID | Utility Project Name or other project completion notes
Site Wide Lighting Project and controls | Lighting | Developing | 600000 | 1130000 | Jan 23'-Nov 23' | Lighting Calculator
Efficient Pump Upgrade | UES | Developing | 50000 | 130000 | Jan 23'-Nov 23' | Prescriptive
VAV addition and Replacement: Building Baseline (install of projects) | Custom | In Progress | 75000 | 800000 | Feb 23'-Oct 23' | Project Assessment Report
Building Commissioning | Custom | In Progress | 135000 | 160000 | Jun 23'-Dec 23' | Project Assessment Report
Chiller and Fan Upgrade | Custom | In Progress | 300000 | 290000 | Apr 23'-June 23' | Scoping Report
Site wide SEM | SEM | Complete | 10000 | 300000 | Jun 23'-Aug 23' | Used cohort average of 2.5%
Total |  |  | 1170000 | 2810000
Note on B8: To add additional rows, right click anywhere in the body of the table and select 'Insert>Table Rows Above'
Note on C8: At least one project must be categorized as an end use other than lighting
Note on F8: The sum of identified energy savings must exceed 200,000 kWh -Savings from lighting projects are obtained from the Utility Lighting Calculator. -Savings from UES are obtained from BPA's UES Measure List -Savings for Custom Projects & SEM projects require a brief description of the approach used to estimate the value in accompanying tab.
Note on H8: -Savings from lighting projects are obtained from the Utility Lighting Calculator. -Savings from UES are obtained from BPA's UES Measure List -Savings estimatesfor Custom Projects & SEM projects require a brief description of the approach used to estimate the value in accompanying tab.
Note on J8: Interpretation of Completion Date may vary by site and utility. However, EPM Payments may only be made on projects that have a 'Completion Date' in BPA's BEETS system
Note on L8: Busbar factor can be entered on 'List' Sheet.
JOB AID NOTES (TO BE DELETED BY USER):
This workbook provides two different versions of the EPM Comprehensive Site Plan template.
1. The simple template 'Comp Plan - Simple' tab meets the minimum requirements of BPA's Implementation Manual.
2. The full template 'Comp Plan - Full Econ' tab includes estimates of avoided cost, project incentives, and EPM payments. Be sure to check the incentive values carefully. Incentive values may need to be overwritten to reflect utility caps or utility-specific payment formulas.
3. Incentive rates should be entered in the 'List' tab
4. To minimize confusion, delete the template version (i.e., 'Comp Plan - Simple' or 'Comp Plan - Full Econ') tab that you will not be using.

## Comp Plan - Full Econ
Acme Incorporated Energy Project Manager Comprehensive Plan |  |  | EPM Name | Jane Smith |  |  |  | EPM Commencement Date | 2023-07-01 |  | Date updated | 2023-07-01
|  |  | EPM Title | Facilities Engineer |  |  |  | Energy Cost ($/kWh) | 0.07
|  |  | Site Name | Acme Incorporated |  |  |  | Baseline Usage (kWh/yr) | 25000000 |  | BEETS App ID | VYPMCR1550500959
Project Planning and Tracking | [12 empty] | Project Completion Information
Project Description | Project Type | Project Status | Est. Project Cost ($) | Est. Savings (kWh/yr) | Est. Utility Incentive | Est. Avoided Cost ($/yr) | Est. EPM Incentive | Total Incentive | Simple Payback (yrs) | Est. Completion Date | Brief Description of Savings Approach | Notes | Completion Date | Verified Site Savings (kWh/yr) | Verified Busbar Savings (kWh/yr) | BEETS Application ID | Utility Project Name or other project completion notes
Site Wide Lighting Project and controls | Custom | Developing | 600000 | 1130000 | 372900 | 79100 | 28250 | 401150 | 2.5139 | Jan 23'-Nov 23'
Efficient Pump Upgrade | Lighting | Developing | 50000 | 130000 |  | 9100 | 3250 | 3250 | 5.1374 | Jan 23'-Nov 23'
VAV addition and Replacement: Building Baseline (install of projects) | Custom | In Progress | 75000 | 800000 | 52500 | 56000 | 20000 | 72500 | 0.044643 | Feb 23'-Oct 23'
Building Commissioning | Custom | In Progress | 135000 | 160000 | 52800 | 11200 | 4000 | 56800 | 6.9821 | Jun 23'-Dec 23'
Chiller and Fan Upgrade | Custom | In Progress | 300000 | 290000 | 95700 | 20300 | 7250 | 102950 | 9.7069 | Apr 23'-June 23'
Total |  |  | 1160000 | 2510000 | 573900 | 175700 | 62750 | 636650
Note on B7: To add additional rows, right click anywhere in the body of the table and select 'Insert>Table Rows Above'
Note on C7: At least one project must be categorized as an end use other than lighting
Note on F7: The sum of identified energy savings must exceed 200,000 kWh -Savings from lighting projects are obtained from the Utility Lighting Calculator. -Savings from UES are obtained from BPA's UES Measure List -Savings for Custom Projects & SEM projects require a brief description of the approach used to estimate the value in accompanying tab.
Note on G7: Incentive rates for Custom Projects may be input in the 'List' tab. For UES, SEM, and Lighting, enter an estimated incentive
Note on I7: Per site, per rate period, the Maximum EPM Incentive shall be the Lesser of: > $0.025/kWh Verified Busbar Savings > $150,000 > A lesser $/kWh cap as designated by your participating Utility
Note on M7: -Savings from lighting projects are obtained from the Utility Lighting Calculator. -Savings from UES are obtained from BPA's UES Measure List -Savings for Custom Projects & SEM projects require a brief description of the approach used to estimate the value in accompanying tab.
Note on O7: Interpretation of Completion Date may vary by site and utility. However, EPM Payments may only be made on projects that have a 'Completion Date' in BPA's BEETS system
Note on Q7: Busbar factor can be entered on 'List' Sheet.
JOB AID NOTES (TO BE DELETED BY USER):
This workbook provides two different versions of the EPM Comprehensive Site Plan template.
1. The simple template 'Comp Plan - Simple' tab meets the minimum requirements of BPA's Implementation Manual.
2. The full template 'Comp Plan - Full Econ' tab includes estimates of avoided cost, project incentives, and EPM payments. Be sure to check the incentive values carefully. Incentive values may need to be overwritten to reflect utility caps or utility-specific payment formulas.
3. Incentive rates should be entered in the 'List' tab
4. To minimize confusion, delete the template version (i.e., 'Comp Plan - Simple' or 'Comp Plan - Full Econ') tab that you will not be using.

## Lists
Busbar Factor from BPA's Implementation Manual
| before 9/30/2023 | effective 10/1/2023
Custom | 1.0906 | 1.1118
Lighting | 1.0748 | 1.1082
*Please refer to BPA's Implementation Manual for official incentive rates and busbar factor
Project Type | $/kWh | Project Cost Cap | Busbar Factor to apply
Custom | 0.33 | 70% | 1.1118
Lighting | per calculator | n/a | 1.1082
UES | n/a | n/a | 1.1118
SEM | 0.04 | n/a | 1.1118
Project Status
Developing
Equipment Order
Equipment Being Installed
Post M&V
Completed
JOB AID NOTES
1. Only edit values in blue fields

## BEETS Entry Job Aid
EPM Application Information
Utility | BEETS App ID | BEETS Project Name
Northern Lights, Inc. | YFPMCR1553119474 | Northern Lights - Alta - Kelley Kimball EPM
Individual Project Information
Utility | BEETS App ID | Project Name | BEETS Status | Completion Date | Savings
Northern Lights, Inc. | YFC1CR1550500890 | Alta Forest Products - Baghouse Upgrades - 3401 | Application Completed | 2023-06-08 | 1025166.75