## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
23-16749 |  | 10/26/2023 07:00 | 06/01/2028 16:00 | VALHALLA: B-280 TERMINAL OF THE VALHALLA-CHELAN CO PUD 115KV FEEDER T1 | VALHALLA: CHELAN CO PUD 115KV FEEDER T1 | CI
24-03472 |  | 01/22/2024 08:00 | 06/22/2025 15:00 | MALIN: PG&E ROUND MOUNTAIN 1 500KV SERIES CAP GRP SEGMENT 1 and 2
24-09008 | 15780159 | 05/06/2024 18:00 | 05/15/2025 15:00 | ROCK CREEK: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1719
24-13186 |  | 08/01/2024 08:00 | 08/01/2025 15:00 | BIG EDDY: PCB A-698 | BIG EDDY: PCB A-698 | COI, NWACI, PDCI, WOJD
25-04441 |  | 02/01/2025 08:00 | 05/19/2025 12:00 | PG&E: TABLE MOUNTAIN SERIES CAPACITOR - ROUND MOUNTAIN NO. 1 |  | COI
25-02242 |  | 03/03/2025 07:00 | 05/04/2025 18:00 | SCL-BOTHELL: PCB 240-72 |  | SOC, NOEL
25-00067 | 16712313 | 03/10/2025 15:00 | 05/30/2025 15:00 | MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP |  | COI
25-05595 | 17482099 | 03/31/2025 10:00 | 05/01/2025 16:00 | -EWEB- WILLAMETTE SUBSTATION INCLUDING UNIVERSITY (EWEB)-WILLAMETTE 115KV LINE AND CURRIN-OAKWAY-WILLAMETTE 115KV LINE | CURRIN-OAKWAY-WILLAMETTE 115KV LINE, UNIVERSITY (EWEB)-WILLAMETTE 115KV LINE, WILLAMETTE: PCB 6050, WILLAMETTE: PCB 6060, WILLAMETTE: PCB 6070, UNIVERSITY EWEB: PCB 7070 | EWEB
25-01365 | 17030311 | 04/01/2025 07:30 | 06/13/2025 16:00 | ALCOA: B-230 TERMINAL OF PIONEER-ALCOA NO 1 115KV LINE | FELIDA-SW48 SECTION OF PIONEER-ALCOA NO 1 115KV LINE, SW48-ALCOA SECTION OF PIONEER-ALCOA NO 1 115KV LINE | LOAD
25-03487 | 17287064 | 04/11/2025 20:00 | 05/02/2025 15:00 | ROSS-ST JOHNS NO 1 230kV LINE INCLUDING ST JOHNS: 230/115KV TRANSFORMER 1 | ST. JOHNS: 230/115KV TRANSFORMER 1, ROSS-ST JOHNS NO 1 230KV LINE, ROSS: PCB A-32, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
25-04376 | 17339873 | 04/14/2025 07:00 | 05/30/2025 16:00 | OLYMPIA: 230/115KV TRANSFORMER 2 RELAYS INCLUDING PCB A-212 AND B-676 RELAYS | OLYMPIA: PCB A-212, OLYMPIA: PCB B-676, OLYMPIA: 230/115KV TRANSFORMER 2 | NOEL, RP, SOC, WOCN
25-00775 |  | 04/14/2025 07:00 | 05/01/2025 17:00 | NORTH BONNEVILLE: A-11 TERMINAL OF THE BONNEVILLE PH-NORTH BONNEVILLE NO 4 230KV LINE | BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE, BONNEVILLE PH: 230/13.8KV BANK 12 | GEN, FCRPS, WOCS
25-04196 |  | 04/14/2025 07:00 | 05/22/2025 16:00 | BROADVIEW SWITCHYARD (NWE)-COLSTRIP A 500KV LINE |  | MT-NW, GEN, STCON
25-01308 | 17055364 | 04/14/2025 08:00 | 05/01/2025 16:30 | VANTAGE: 500/230KV TRANSFORMER 1, INCLUDING AUX BUS SECTION 2 |  | GEN, NOH, SIG, WI
25-01317 | 17031281 | 04/14/2025 08:00 | 05/01/2025 15:00 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP | ROSS: PCB A-22, NORTH BONNEVILLE: PCB A-14, SIFTON: PCB B-1511, SIFTON: 230KV WEST MAIN BUS, SIFTON: 230KV AUX BUS, SIFTON: 230/115KV TRANSFORMER 1, NORTH BONNEVILLE-ROSS NO 2 230KV LINE, SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 2 230KV LINE | SOA, NOPE, WOCS, GEN, LOAD, FCRPS
25-01323 | 17031197 | 04/14/2025 08:00 | 05/01/2025 15:00 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | TROUTDALE: PCB A-125, NORTH BONNEVILLE: PCB A-16 | GEN, LOAD, WOCS, FCRPS
25-02179 | 17524582 | 04/17/2025 17:00 | 05/09/2025 16:00 | ASHE: PCB A-809 |  | NOH
25-02178 | 17524540 | 04/17/2025 17:00 | 05/09/2025 16:00 | ASHE: A-809 TERMINAL OF THE COLUMBIA GENERATING STATION-ASHE #2 230kV LINE | ASHE: PCB A-809, COLUMBIA GENERATING STATION-ASHE NO 2 230KV LINE | NOH, GEN, SIG
25-00391 | 17094634 | 04/18/2025 07:30 | 05/09/2025 17:00 | MIDWAY-HEW NO 1 230kV LINE INCLUDING ASH TAP, ASHE: PCB A-401, A6-ASH TAP SECTION OF MIDWAY-HEW NO 2 230KV LINE, -NEW- MIDWAY-ASHE NO 1 230KV LINE AND MIDWAY: -NEW-PCB A-1000 | MIDWAY-HEW NO 1 230KV LINE, ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE, A-6-ASHE TAP SECTION OF MIDWAY-HEW NO 2 230KV LINE, ASHE: PCB A-401, MIDWAY: PCB A-1000, MIDWAY: PCB A-336 | GEN, TCLA, LOAD, NOH, WOM
24-05832 |  | 04/21/2025 07:00 | 05/30/2025 16:00 | COLUMBIA: 230/115KV TRANSFORMER 2 |  | LOAD, WOCN, CI, NOH
25-03624 | 17293824 | 04/21/2025 08:00 | 10/06/2025 11:00 | CARDWELL: B-1540 TERMINAL OF CARDWELL-MEEKER 115KV LINE | CARDWELL-MEEKER 115KV LINE, CARDWELL: PCB B-1540 | LOAD, SOA, NOPE
24-03229 | 15417738 | 04/21/2025 08:00 | 05/01/2025 15:00 | CONDON-FOSSIL SECTION OF DE MOSS-FOSSIL NO 1 115KV LINE |  | BGEDY
25-04943 | 17405830 | 04/21/2025 08:00 | 05/30/2025 16:00 | COLUMBIA: PCB B-314 RELAYS, CONTROL CIRCUITS, AND ALARM WIRING
25-04942 | 17405795 | 04/21/2025 08:00 | 05/30/2025 16:00 | COLUMBIA: PCB A-156 RELAYS, CONTROL CIRCUITS, AND ALARM WIRING
25-00503 | 16976449 | 04/21/2025 08:00 | 05/02/2025 16:00 | ALLSTON: 500/230KV TRANSFORMER 2 |  | SIG, SOA, NOPE
24-09780 | 17405757 | 04/21/2025 08:00 | 05/30/2025 15:00 | COLUMBIA: PCB A-170 RELAYS, CONTROL CIRCUITS, AND ALARM WIRING
25-00204 | 17055249 | 04/22/2025 08:00 | 05/27/2025 15:00 | FERN HILL-ASTORIA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE |  | SOA, NOPE
25-02062 | 17424766 | 04/22/2025 09:00 | 05/02/2025 15:00 | UNITY: PCB B-1750 LINE RELAYS | UNITY: PCB B-1750, UNITY-PACIFIC SECTION OF UNITY-WEST BURLEY NO 1 138KV LINE | LOAD, BUHM
25-00433 | 16413680 | 04/28/2025 06:00 | 05/01/2025 17:00 | ECHO LAKE-MONROE NO 1 500KV LINE, INCLUDING SNO-KING TAP | SNO-KING-MONROE SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE-SNO-KING SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, SNO-KING TAP TO ECHO LAKE-MONROE NO 1 500KV LINE | IROL, NI, NOEL, SIG, SOC, WOCN, NOH, BCHT, BCHW
25-01553 | 17324021 | 04/28/2025 07:00 | 05/01/2025 15:00 | BADGER CANYON: PCB B-255
25-00101 |  | 04/28/2025 07:00 | 05/09/2025 14:00 | GARRISON: RAS WM-A CONTROLLER |  | MT-NW, GEN, SIG, WOH
25-01078 |  | 04/28/2025 08:00 | 05/02/2025 16:00 | ALVEY: PCB A-652 AND 230/115KV TRANSFORMER 4 CONTROL AND ALARM CIRCUITS | ALVEY: 230/115KV TRANSFORMER 4, ALVEY: PCB A-652 | SCORC, EWEB, NWACI
25-04055 | 17319534 | 04/28/2025 08:00 | 05/08/2025 15:00 | JOHN DAY: PCB 4176 SEL BFR AND BREAKER DIFF | JOHN DAY: PCB 4176 | NWACI, WOJD, PDCI
24-08699 | 15696119 | 04/28/2025 08:00 | 05/01/2025 15:00 | COLUMBIA FALLS: 230/115KV TRANSFORMER 3 |  | WOCN, FLAT
24-16020 | 17042709 | 04/28/2025 08:00 | 05/01/2025 16:00 | TILLAMOOK: 230/115KV TRANSFORMER 2 | TILLAMOOK: PCB B-1098 | LOAD, SOA, NOPE
25-00454 | 16834745 | 04/28/2025 08:00 | 05/09/2025 15:00 | MALIN: 500KV REACTOR 1 INCLUDING PCB 4327 | MALIN: PCB 4327, MALIN: 500KV REACTOR 1 | COI, NWACI
25-00176 | 16227917 | 04/28/2025 08:00 | 05/08/2025 17:00 | PILOT BUTTE-LAPINE NO 1 230KV LINE | LAPINE: PCB A-1552 | COR, NWACI
25-02315 | 17181686 | 04/28/2025 08:00 | 05/01/2025 15:00 | PONDEROSA: PACW 230KV FEEDER 1 INCLUDING PONDEROSA: PCB'S A-384 & A-395 | PONDEROSA: PACIFICORP (PACW) 230KV FEEDER 1, PONDEROSA: 230KV GIS NORTH BUS SECTION, PONDEROSA: PCB A-384, PONDEROSA: PCB A-395 | LOAD, COR, NWACI
25-00957 | 16898684 | 04/28/2025 08:00 | 05/02/2025 15:00 | MARION-ALVEY NO 1 500KV LINE, INCLUDING ALVEY: PCB 5081, PCB 5084 AND MARION 1 500KV LINE SERIES CAP GROUP 1 | ALVEY: PCB 5081, ALVEY: PCB 5084, ALVEY: MARION 1 500KV LINE SERIES CAP GROUP 1 | BCHT, BCHW, NI, NWACI, SIG, EWEB
25-04093 | 17455220 | 04/28/2025 08:00 | 05/01/2025 15:00 | SNO-KING: 230/115KV TRANSFORMER 3 INCLUDING PCBS A-1200 AND B-1706 | SNO-KING: 230/115KV TRANSFORMER 3, SNO-KING: PCB A-1200, SNO-KING: PCB B-1706 | LOAD, NOEL, SOC, BCHT, BCHW
25-00912 | 17042488 | 04/28/2025 08:00 | 05/01/2025 15:00 | CARLTON-TILLAMOOK NO 1 230KV LINE | TILLAMOOK: 230/115KV TRANSFORMER 2, TILLAMOOK: PCB B-1098, CARLTON: PCB A-315 | LOAD, SOA, NOPE, NWACI
25-02698 |  | 04/28/2025 09:00 | 05/02/2025 14:00 | -IPCO- AMERICAN FALLS: PCB 105A | MINIDOKA PH-AMERICAN FALLS 138KV LINE
25-04912 |  | 04/28/2025 09:00 | 05/02/2025 14:00 | -MITIGATION- UNITY: PCB B-1728 | UNITY-PACIFIC SECTION OF UNITY-WEST BURLEY NO 1 138KV LINE
25-01054 | 16956932 | 04/30/2025 07:00 | 05/01/2025 16:00 | ASHE: PCB 4898 |  | NWACI, FCRPS
25-05878 | 17503957 | 04/30/2025 07:00 | 09/22/2025 17:00 | THE DALLES PH: 230/13.2KV BANK 11
25-00268 | 17035760 | 04/30/2025 08:00 | 05/29/2025 15:00 | RED MOUNTAIN-RUPPERT ROAD SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE INCLUDING B-2110 LINE DISCONNECT
25-03027 | 17246717 | 05/01/2025 08:00 | 05/01/2025 11:00 | CAL YOUNG: PCB 4872 | CAL YOUNG-SANTA CLARA 115KV LINE | EWEB
24-06659 | 17050101 | 05/01/2025 08:00 | 05/01/2025 15:00 | PEARL: 230KV WEST MAIN BUS INCLUDING PCB A-1192 | PEARL: PCB A-1192, PEARL: PCB A-1166, PEARL-SHERWOOD NO 1&2 230KV LINE, PEARL: PCB A-1167, PEARL: 230KV AUX BUS, PEARL: PCB A-1190, PEARL: 500/230KV TRANSFORMER 2, PEARL: 230KV WEST MAIN BUS | SOA, NOPE, LOAD, WOCS, SIG
25-02846 | 17332642 | 05/01/2025 08:00 | 05/01/2025 15:00 | SATSOP: PCB A-622 |  | GEN, LOAD
25-00781 | 16771171 | 05/01/2025 10:00 | 05/11/2025 17:00 | -EWEB- ENID RD-PRAIRIE (EWEB)-SPRING CREEK (EWEB) 115KV LINE INCLUDING SENECA SAWMILL | ENID RD-PRAIRIE (EWEB)-SPRING CREEK (EWEB) 115KV LINE | EWEB
25-03489 | 17287068 | 05/03/2025 08:00 | 05/17/2025 15:00 | ST JOHNS-KEELER NO 2 115KV LINE INCLUDING KEELER: PCB B-1072 | ST JOHNS: PCB B-42, KEELER: PCB B-1072, ST JOHNS-KEELER NO 2 115KV LINE | LOAD, SOA, NOPE
25-04069 | 17320344 | 05/03/2025 08:00 | 05/03/2025 14:30 | KEELER: 115KV AUX BUS | KEELER: PCB B-1076
25-05997 | 17517868 | 05/04/2025 21:00 | 05/05/2025 06:00 | KEELER-ALLSTON NO 1 500KV LINE |  | SIG, SOA, WOCS, NOPE
25-00937 | 16835625 | 05/05/2025 07:00 | 05/23/2025 15:00 | SNOHOMISH-MURRAY NO 1 230KV LINE |  | NOEL, SOC
25-04821 | 17406456 | 05/05/2025 07:00 | 05/05/2025 12:00 | COLUMBIA: 115KV AUX BUS | COLUMBIA: PCB B-398
25-00580 | 17319888 | 05/05/2025 07:00 | 05/08/2025 14:00 | GARRISON: PCB 4421, PCB 4418, MOD 4420, MOD 4419, BROADVIEW 1 500KV LINE SERIES CAP GROUP 1, PCB 4469, 500KV REACTOR 1 CONTROL AND ALARM CIRCUITS (FORCES OUT BROADVIEW-GARRISON NO 1 500KV LINE) | GARRISON: PCB 4418, GARRISON: PCB 4421, GARRISON: PCB 4469, GARRISON: 500KV REACTOR 1, BROADVIEW-GARRISON NO 1 500KV LINE, GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, GEN
25-03584 | 17299317 | 05/05/2025 07:00 | 05/13/2025 16:00 | GRAND COULEE-NILLES CORNER SECTION OF GRAND COULEE-FOSTER CREEK NO 1 115KV LINE
25-02454 | 17379290 | 05/05/2025 07:00 | 05/08/2025 14:00 | GARRISON: 230KV WEST MAIN BUS SECTION INCLUDING PCBs A-875 AND A-876 | GARRISON-NWE MILL CREEK NO 1 230KV LINE | MT-NW
25-01055 | 16956938 | 05/05/2025 07:00 | 05/06/2025 16:00 | ASHE: PCB 5327 |  | GEN, NWACI, WOLM, FCRPS
25-04803 | 17380715 | 05/05/2025 07:30 | 05/08/2025 15:30 | ROSS: 230/115KV TRANSFORMER 2 RELAYS | ROSS: 230/115KV TRANSFORMER 2 | LOAD, SOA, NOPE
25-04940 | 17405847 | 05/05/2025 08:00 | 05/15/2025 16:00 | COLUMBIA: PCB B-398 RELAYS, CONTROL CIRCUITS, AND ALARM WIRING | COLUMBIA: PCB B-398
25-01461 |  | 05/05/2025 08:00 | 05/22/2025 15:00 | ALVEY: PCB B-586 RELAYS | ALVEY: PCB B-586
25-05359 |  | 05/05/2025 08:00 | 05/09/2025 18:00 | SCL - EAST PINE-DENNY 120KV LINE INCLUDING EAST PINE: 240/120 KV BANK 95 |  | SOC/NOEL
25-00850 | 16814483 | 05/05/2025 08:00 | 05/06/2025 15:00 | SLATT: PCB A-1801 BFR | SLATT: PCB A-1801 | WOJD, NWACI
25-01309 | 17055450 | 05/05/2025 08:00 | 05/15/2025 16:30 | VANTAGE: 500/230KV TRANSFORMER 2 |  | GEN, NOH, SIG, WI
25-00538 | 16584710 | 05/05/2025 08:00 | 05/08/2025 15:00 | MARION: 500KV CAP GROUP 1 INCLUDING PCB 4331 | MARION: 500KV CAP GROUP 1, MARION: PCB 4331 | WOCS, NWACI
25-00201 | 16054490 | 05/05/2025 08:00 | 05/15/2025 15:00 | MCNARY: 500/230KV TRANSFORMER 2 |  | WOM, NWACI
25-02214 |  | 05/05/2025 08:00 | 05/08/2025 16:30 | CHENOWETH-SPEARFISH SECTION OF CHENOWETH-GOLDENDALE NO 1 115KV LINE |  | GEN, WOM
25-02799 | 17332651 | 05/05/2025 08:00 | 05/06/2025 15:00 | SATSOP: PCB A-681 |  | GEN, LOAD
25-02319 | 17181756 | 05/05/2025 08:00 | 05/08/2025 17:00 | PONDEROSA: 230KV INTERCONNECT BUS SECTION INCLUDING PCB'S A-395, A-398, A-1815 AND A-1818 | PONDEROSA: 230KV INTERCONNECT GIS BUS SECTION, PONDEROSA: 230KV INTERCONNECT NON-GIS BUS SECTION, PONDEROSA: PCB A-395, PONDEROSA: PCB A-398, PONDEROSA: PCB A-1815, PONDEROSA: PCB A-1818 | LOAD, COR, NWACI, SIG
25-01067 | 17068922 | 05/05/2025 08:00 | 05/08/2025 15:00 | CANAL-EAST HILLS SECTION OF MINIDOKA PH-UNITY NO 1 138KV LINE
25-01224 |  | 05/05/2025 08:00 | 05/10/2025 17:00 | -PACWEST- WARRENTON TAP-ASTORIA SECTION OF THE SEASIDE-ASTORIA #1 115KV LINE |  | SOA
25-04572 | 17368454 | 05/05/2025 08:30 | 05/05/2025 15:00 | FAIRMOUNT: LBD A-1628 | FAIRMOUNT: 230KV CAP GROUP 2, FAIRMOUNT: LBD A-1628 | RP
25-04924 | 17406712 | 05/05/2025 12:00 | 05/15/2025 08:00 | COLUMBIA: PCB B-398 INCLUDING B-398 MAIN BUS AND AUX BUS DISCs | COLUMBIA: PCB B-398
25-04823 | 17406516 | 05/05/2025 12:00 | 05/05/2025 17:00 | COLUMBIA: 115KV SOUTH MAIN BUS INCLUDING PCB B-398 | COLUMBIA-B408 SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, COLUMBIA-ROCKY FORD NO 1 115KV LINE, COLUMBIA: 230/115KV TRANSFORMER 1, COLUMBIA: 115KV SOUTH MAIN BUS | TCLA, NOH, LOAD, WOCN, CI
25-06129 |  | 2025-05-05 07:00 | 2025-06-06 17:00 | MIDPOINT (IPC)-HEMINGWAY 500KV LINE | IPC WORK-INSTALL CCVT ON WEST BUS OF 544D
25-04479 | 17367378 | 05/06/2025 07:00 | 05/06/2025 15:00 | BELLINGHAM: 230/115KV TRANSFORMER 1 INCLUDING 115KV AUX BUS | BELLINGHAM: 13.8KV PCB L-1118, BELLINGHAM: 230/115KV TRANSFORMER 1 | LOAD, NOEL, SOC
25-05387 | 17457461 | 05/06/2025 07:00 | 05/06/2025 15:00 | MURRAY: PCB A-1516 |  | BCHT, BCHW, NOEL, SOC
25-00848 | 16834370 | 05/06/2025 07:30 | 05/07/2025 16:00 | OSTRANDER: PCB 4450 |  | WOCS
25-00902 | 16840196 | 05/06/2025 07:30 | 05/06/2025 07:45 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-04953 | 17401186 | 05/06/2025 08:00 | 05/06/2025 15:00 | MINT FARM-LONGVIEW NO 1 230KV LINE MBTT | MINT FARM-LONGVIEW NO 1 230KV LINE, LONGVIEW: PCB A-1380, LONGVIEW: 230KV NORTH AUX BUS, LONGVIEW: PCB A-1378 | SOA, LOAD, NOPE
25-04573 |  | 05/06/2025 09:30 | 05/06/2025 15:00 | KITSAP: LBD B-998
25-00903 | 16840202 | 05/06/2025 11:15 | 05/06/2025 11:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-05998 | 17517871 | 05/06/2025 21:00 | 05/07/2025 06:00 | KEELER-ALLSTON NO 1 500KV LINE |  | SIG, SOA, WOCS, NOPE
25-05389 | 17457468 | 05/07/2025 07:00 | 05/07/2025 15:00 | MURRAY: PCB A-1510 | MURRAY: PCB A-1516 | BCHT, BCHW, NOEL, SOC
25-01056 | 16956951 | 05/07/2025 07:00 | 05/08/2025 16:00 | ASHE: PCB 5324 |  | GEN, NWACI, FCRPS
25-00694 | 16807942 | 05/07/2025 07:30 | 05/07/2025 15:30 | MURRAY: 115KV CAP GROUP 1 SECTION 1 AND 2 INCLUDING PCB B-1745 | MURRAY: 115KV CAP GROUP 1 SECTION 1, MURRAY: 115KV CAP GROUP 1 SECTION 2, MURRAY: PCB B-1745
25-00851 | 16814611 | 05/07/2025 08:00 | 05/08/2025 15:00 | SLATT: PCB A-1804 BFR | SLATT: PCB A-1804 | WOJD, NWACI
25-04388 | 17343918 | 05/07/2025 08:00 | 05/08/2025 15:00 | FLATHEAD: PCB A-1957 | FLATHEAD: 230KV AUX BUS
25-00539 | 16835418 | 05/07/2025 08:00 | 05/07/2025 15:00 | PEARL-KEELER NO 1 500KV LINE INCLUDING PEARL: MOD'S 4281 AND 4282 | PEARL-KEELER NO 1 500KV LINE, PEARL: MOD 4281, PEARL: MOD 4282, PEARL: PCB 4280, PEARL: PCB 4283 | SIG, SOA, NOPE, NWACI
25-02800 | 17332656 | 05/07/2025 08:00 | 05/08/2025 15:00 | SATSOP: PCB A-678 |  | GEN, LOAD
25-05395 | 17457503 | 05/08/2025 07:00 | 05/08/2025 15:00 | MURRAY: PCB B-1749 | MURRAY: PCB B-1745, MURRAY: 115KV CAP GROUP 1 SECTION 1, MURRAY: 115KV CAP GROUP 1 SECTION 2
25-02217 | 17221581 | 05/09/2025 22:00 | 05/10/2025 08:00 | LYLE TAP INCLUDING -KPUD-KB1299 DISC OF CHENOWETH-GOLDENDALE NO 1 115KV LINE | CHENOWETH-SPEARFISH SECTION OF CHENOWETH-GOLDENDALE NO 1 115KV LINE, SPEARFISH TAP TO CHENOWETH-GOLDENDALE NO 1 115KV LINE, LYLE TAP TO CHENOWETH-GOLDENDALE NO 1 115KV LINE | GEN, WOM
25-05847 | 17496614 | 05/10/2025 06:30 | 05/10/2025 15:00 | GRAND COULEE: PCBS 6182 AND 6382 | GRAND COULEE: PCB 6382, GRAND COULEE: PCB 6182 | NOH, WOCN
25-05367 |  | 05/10/2025 08:00 | 05/11/2025 18:00 | SCL - UNION-BROAD 120KV LINE INCLUDING UNION: BANK 7 AND 120KV BUS 1 |  | SOC/NOEL
25-00102 |  | 05/12/2025 07:00 | 05/23/2025 14:00 | GARRISON: RAS WM-B CONTROLLER |  | MT-NW, GEN, SIG, WOH
25-00581 | 17319741 | 05/12/2025 07:00 | 05/15/2025 14:00 | GARRISON: PCB 4360, PCB 4463, MOD 4361, MOD 4464, TAFT 2 500KV LINE SERIES CAP GROUP 2, PCB 4458 CONTROL AND ALARM CIRCUITS (FORCES OUT GARRISON-TAFT 2 500KV LINE) | GARRISON: PCB 4360, TAFT: PCB 4125, TAFT: PCB 4148, GARRISON: PCB 4463, GARRISON: HSGS 7883, GARRISON: PCB 4458, GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2, GARRISON-TAFT NO 2 500KV LINE, TAFT: HSGS 7882 | MT-NW, WOH, SIG
24-14584 |  | 05/12/2025 07:00 | 05/30/2025 14:30 | PAC - COPCO-KLAMATH FALLS 230KV LINE |  | NWACI/PDCI
25-03514 | 17298719 | 05/12/2025 07:00 | 05/27/2025 14:00 | HUNGRY HORSE-COLUMBIA FALLS NO 1 230KV LINE |  | GEN, MT-NW, FLAT
25-00867 | 16835527 | 05/12/2025 07:00 | 05/13/2025 15:00 | PAUL: PCB 4540 |  | WOCS, SOA, NOPE
25-06097 | 17525399 | 05/12/2025 07:00 | 05/22/2025 16:00 | LONGVIEW: B-331 TERMINAL OF LONGVIEW-MINT FARM NO 1 115KV LINE | LONGVIEW-MINT FARM NO 1 115KV LINE, LONGVIEW: PCB B-331 | GEN, STCON
25-02192 | 17191426 | 05/12/2025 07:00 | 05/21/2025 16:00 | GRAND COULEE-SCHULTZ NO 1 500KV LINE | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 | IROL, NOEL, NOH, SOC, WOCN, GEN, SIG, FCRPS
25-04603 |  | 05/12/2025 07:30 | 05/22/2025 16:00 | MARTIN CREEK-DRAIN NO 1 115KV LINE | DRAIN: DOUGLAS ELEC COOP 69KV FEEDER 1 TO OAKLAND | SCORC
25-00852 | 16818940 | 05/12/2025 07:30 | 05/15/2025 16:00 | OSTRANDER: 500/230KV TRANSFORMER 1 | OSTRANDER: PCB 4442, OSTRANDER: PCB 4445, OSTRANDER-MCLOUGHLIN NO 1 230KV LINE | SIG, SOA, WOCS, NOPE, LOAD
25-02320 | 17287714 | 05/12/2025 08:00 | 05/15/2025 17:00 | PONDEROSA: PCB A-398 |  | SIG, COR, NWACI
25-04605 | 17373402 | 05/12/2025 08:00 | 05/15/2025 15:00 | JONES CANYON-TUMBLE CREEK SECTION OF JONES CANYON-SANTIAM NO 1 230KV LINE | JONES CANYON-SANTIAM NO 1 230KV LINE | GEN, WOCS, WOM, SOA, NOPE
25-02197 | 17177174 | 05/12/2025 08:00 | 05/30/2025 15:00 | COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 4694 | COLUMBIA: PCB 4694, COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 | NOH, WOCN, IROL, NOEL, SOC
25-01225 |  | 05/12/2025 08:00 | 05/17/2025 17:00 | -PACWEST- WARRENTON TAP-ASTORIA SECTION OF THE SEASIDE-ASTORIA #1 115KV LINE
25-02223 |  | 05/12/2025 08:00 | 05/22/2025 16:30 | SPEARFISH-E. E. CLOUSE SECTION OF CHENOWETH-GOLDENDALE NO 1 115KV LINE
25-00177 | 16208136 | 05/12/2025 08:00 | 05/22/2025 15:30 | MAUPIN-REDMOND NO 1 230KV LINE | MAUPIN: PCB A-843, REDMOND: PCB A-265 | COR, NOH, GRZN, NWACI
25-00392 | 16382017 | 05/12/2025 08:00 | 05/15/2025 16:30 | RAVER-PAUL NO 1 500KV LINE | RAVER: PCB 4879, RAVER: PCB 4876, PAUL: PCB 4532, PAUL: PCB 4530 | BCHT, BCHW, IROL, NI, NOH, RP, SIG, SOA, SOC, NOEL, WOCN, NOPE, NWACI, WOCS, GEN
24-00465 | 15184009 | 05/12/2025 08:00 | 05/22/2025 15:00 | CHEMAWA: 230/115KV TRANSFORMER 2 | CHEMAWA: 230/115KV TRANSFORMER 2, CHEMAWA: PCB A-339, CHEMAWA: PCB B-108 | WOCS, LOAD, SLAL
25-00960 |  | 05/12/2025 08:00 | 05/18/2025 16:00 | MCMINNVILLE: PCB B-381
25-02089 | 17264195 | 05/12/2025 08:00 | 05/15/2025 15:00 | SHELTON-T3BA'DAS SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE
25-03610 | 17293382 | 05/12/2025 08:00 | 05/12/2025 08:30 | PEARL: 500KV EAST BUS | PEARL: 500KV CAP GROUP 1 | WOCS, SOA, NOPE, NWACI
25-01216 | 17074799 | 05/12/2025 08:00 | 05/30/2025 15:00 | SANDHILL CRANE-FIRST STREET SECTION OF WHITE BLUFFS-RICHLAND NO 1 115KV LINE INCLUDING FIRST STREET B-1061 DISCONNECT | FIRST STREET: CITY OF RICHLAND 115KV FEEDER 2, SAND HILL CRANE-FIRST STREET SECTION OF WHITE BLUFFS-RICHLAND NO 1 115KV LINE | TCLA
25-03400 | 17292659 | 05/12/2025 08:00 | 05/12/2025 12:00 | PEARL: 500/230KV TRANSFORMER 1 | PEARL: PCB A-1169 | LOAD, SIG, SOA, WOCS, NOPE
25-05388 |  | 05/12/2025 08:00 | 05/15/2025 18:00 | SCL - NORTH-UNION 120KV LINE INCLUDING NORTH:120KV BUS 3, PCB'S 120-76 & -77 |  | SOC/NOEL
25-04576 | 17368724 | 05/12/2025 08:30 | 05/12/2025 15:30 | KITSAP: PCB B-969 |  | LOAD
25-03612 | 17293379 | 05/12/2025 11:30 | 05/12/2025 12:00 | PEARL: 500KV EAST BUS | PEARL: 500KV CAP GROUP 1 | WOCS, SOA, NOPE, NWACI
25-05547 | 17475483 | 05/13/2025 07:30 | 05/17/2025 16:00 | ST JOHNS-DUTCH CANYON SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE |  | LOAD, SOA, NOPE
25-00877 | 16840207 | 05/13/2025 07:30 | 05/13/2025 07:45 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-02255 | 17160281 | 05/13/2025 08:00 | 05/13/2025 15:00 | CUSTER: PCB A-1238 |  | BCHT, BCHW, NOEL, SOC, NI
25-01118 | 17049753 | 05/13/2025 08:00 | 05/14/2025 16:00 | DRISCOLL: PCB A-1264 | DRISCOLL TAP TO ALLSTON-CLATSOP NO 1 230KV LINE | SOA, NOPE
25-01068 | 17074912 | 05/13/2025 08:00 | 05/13/2025 15:00 | EAST HILLS-UNITY SECTION OF MINIDOKA PH-UNITY NO 1 138KV LINE
25-00879 | 16840208 | 05/13/2025 11:15 | 05/13/2025 11:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-03117 | 17264345 | 05/14/2025 06:00 | 05/15/2025 15:00 | DRUMMOND: 115KV MAIN BUS INCLUDING PCBS B-1682, B-1683, B-1686, B-1831, B-1681, B-1502 AND 115KV CAP GROUPS 1 AND 2 | DRUMMOND: 115KV MAIN BUS, DRUMMOND: 115KV CAP GROUP 1, DRUMMOND: 115KV CAP GROUP 2, DRUMMOND: 115/46KV TRANSFORMER 1, DRUMMOND: 115/46KV TRANSFORMER 3, DRUMMOND: 161/115KV TRANSFORMER 4, DRUMMOND: 46KV PCB L-1736, DRUMMOND: 46KV PCB L-1742, DRUMMOND: PCB B-1502, DRUMMOND: PCB B-1681, DRUMMOND: PCB B-1682, DRUMMOND: PCB B-1683, DRUMMOND: PCB B-1684, DRUMMOND: PCB B-1686, GOSHEN-DRUMMOND NO 1 161KV LINE, DRUMMOND: FALL RIVER E COOP 46KV FEEDER 1, DRUMMOND: FALL RIVER E COOP 46KV FEEDER 2, DRUMMOND: FALL RIVER E COOP 46KV XFMR 2 FEEDER | LOAD, SEIL, GEN
25-04881 | 17407115 | 05/14/2025 07:00 | 05/14/2025 15:00 | COLUMBIA: 115KV SOUTH MAIN BUS INCLUDING PCB B-398 AND NEW B-398 M/B AND A/B DISCs | COLUMBIA: 115KV SOUTH MAIN BUS, COLUMBIA: 230/115KV TRANSFORMER 1, COLUMBIA-B408 SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, COLUMBIA-ROCKY FORD NO 1 115KV LINE | TCLA, CI, NOH, LOAD, WOCN
25-04879 | 17406741 | 05/15/2025 07:00 | 05/15/2025 15:00 | COLUMBIA: 115KV AUX BUS
25-02639 | 17209531 | 05/15/2025 08:00 | 05/15/2025 12:00 | LANCASTER-RATHDRUM POWER NO 1 230KV LINE INCLUDING LANCASTER: PCB'S A-1182 AND A-1561 | LANCASTER-RATHDRUM POWER NO 1 230KV LINE, LANCASTER: PCB A-1182, LANCASTER: PCB A-1561 | WOH
25-03377 |  | 05/15/2025 10:00 | 05/15/2025 12:00 | NINE MILE: PCB 52-U3 BFR RELAY | NINE MILE: PCB 52-U3, NINE MILE: PCB 52-M3, NINE MILE: FPL ENERGY VAN 115KV FEEDER 1
25-02090 | 17264258 | 05/16/2025 08:00 | 05/22/2025 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE |  | PA
25-01313 |  | 05/18/2025 22:00 | 05/18/2025 22:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-00606 |  | 05/19/2025 06:00 | 06/20/2025 16:00 | -OTEC- HINES-WEST JOHN DAY 138KV LINE
25-04754 |  | 05/19/2025 06:00 | 05/23/2025 16:30 | PACW:GRANTS PASS-GLENDALE SECTION OF THE GRANTS PASS-DIXONVILLE 230KV LINE
25-01213 | 16965057 | 05/19/2025 07:00 | 05/20/2025 16:00 | COYOTE SPRINGS: PCB 5190 |  | WOLM, WOM
25-04401 | 17343927 | 05/19/2025 07:00 | 05/19/2025 15:00 | FLATHEAD: PCB A-217 |  | MT-NW, FLAT
25-00582 | 16835596 | 05/19/2025 07:00 | 05/23/2025 16:00 | PAUL: PCB 4808 INCLUDING 500 KV REACTOR NO 1 | PAUL: PCB 4808, PAUL: 500KV REACTOR 1
25-02821 | 17221140 | 05/19/2025 07:00 | 05/19/2025 11:00 | COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTIONS 1, 2, AND 3 INCLUDING PCB A-999, PCB A-1005, PCB A-1007, PCB A-1003 AND 230KV REACTOR 1 | COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 1, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 2, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 3, COVINGTON: 230KV REACTIVE GROUP 1 REACTOR 1, COVINGTON: PCB A-999, COVINGTON: PCB A-1005, COVINGTON: PCB A-1007, COVINGTON: PCB A-1003, COVINGTON: PCB A-1004 | NOEL, SOC, WOCN, LOAD, RP
25-00871 | 16835653 | 05/19/2025 07:30 | 05/20/2025 16:00 | OSTRANDER: 500KV REACTOR NO 1 AND 2 INCLUDING PCB 4838 | OSTRANDER: 500KV REACTOR 1, OSTRANDER: 500KV REACTOR 2, OSTRANDER: PCB 4838 | WOCS
25-01289 | 17075304 | 05/19/2025 07:30 | 05/22/2025 15:00 | GOSHEN-DRUMMOND NO 1 161KV LINE INCLUDING DRUMMOND: 161/115KV TRANSFORMER 4, PCB B-1831 AND THE 115KV AUX BUS | DRUMMOND: 161/115KV TRANSFORMER 4, GOSHEN-DRUMMOND NO 1 161KV LINE, DRUMMOND: PCB B-1831, DRUMMOND: 115KV AUX BUS | GEN, LOAD, SEIL
25-01290 | 17075357 | 05/19/2025 07:30 | 05/22/2025 15:00 | SWAN VALLEY-GOSHEN NO 1 161KV LINE INCLUDING SWAN VALLEY: 161/115KV TRANSFORMER 3 AND STATION SERVICE TRANSFORMER 1 | SWAN VALLEY: 161/115KV TRANSFORMER 3, SWAN VALLEY-GOSHEN NO 1 161KV LINE | SEIL, GEN, LOAD
25-04646 | 17374036 | 05/19/2025 08:00 | 05/22/2025 15:00 | BUCKLEY: A-40 TERMINAL OF JONES CANYON-SANTIAM 1 230KV LINE | BUCKLEY: A-40 STATION SERVICE DISC
25-04606 | 17373369 | 05/19/2025 08:00 | 05/22/2025 15:00 | JONES CANYON-TUMBLE CREEK SECTION OF JONES CANYON-SANTIAM NO 1 230KV LINE | JONES CANYON-SANTIAM NO 1 230KV LINE | GEN, WOCS, WOM, SOA, NOPE
25-04059 | 17320365 | 05/19/2025 08:00 | 06/13/2025 15:00 | KEELER: PCB A-873 INCLUDING 230KV REACTIVE GROUP 2 REACTOR 1 | KEELER: PCB A-873, KEELER: 230KV REACTIVE GROUP 2 REACTOR 1 | SOA, NOPE
25-00845 | 16929391 | 05/19/2025 08:00 | 05/23/2025 15:00 | ALVEY: PCB 5081 |  | NWACI, EWEB
25-03869 | 17304360 | 05/19/2025 08:00 | 05/20/2025 15:00 | ELLENSBURG: 115KV CAP GROUP 1 INCLUDING PCB B-183 | ELLENSBURG: 115KV CAP GROUP 1, ELLENSBURG: PCB B-183 | TCLA
25-00393 | 16382019 | 05/19/2025 08:00 | 05/22/2025 16:30 | RAVER-PAUL NO 1 500KV LINE | RAVER: PCB 4879, RAVER: PCB 4876, PAUL: PCB 4532, PAUL: PCB 4530 | BCHT, BCHW, IROL, NI, NOH, RP, SIG, SOA, SOC, NOEL, WOCN, NOPE, NWACI, WOCS, GEN
25-05392 |  | 05/19/2025 08:00 | 05/23/2025 18:00 | SCL - NORTH: 120KV BUS 4, BANK 54 AND PCB'S 120-77 & -79
25-02348 | 17263235 | 05/19/2025 08:30 | 05/20/2025 17:00 | LAPINE: PCB A-1553 | LAPINE: 230/115KV TRANSFORMER 2 | COR, NWACI, GRZN
25-00904 | 16840301 | 05/20/2025 07:30 | 05/20/2025 07:45 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-02807 | 17220492 | 05/20/2025 08:00 | 05/20/2025 15:00 | TACOMA: 230KV CAP GROUP 3, SECTIONS 1 & 2, INCLUDING 230KV REACTIVE BUS & LBD'S A-1078, A-1079 | TACOMA: 230KV CAP GROUP 3 SECTION 1, TACOMA: 230KV CAP GROUP 3 SECTION 2, TACOMA: 230KV REACTIVE BUS, TACOMA: LBD A-1078, TACOMA: LBD A-1079, TACOMA: PCB A-1062 | NOEL, RP, SOC, WOCN
25-00905 | 16840345 | 05/20/2025 11:15 | 05/20/2025 11:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-00372 | 17268608 | 05/21/2025 06:30 | 05/21/2025 19:00 | KETTLE FALLS-REPUBLIC SECTION OF COLVILLE-REPUBLIC 1 115KV LINE INCLUDING KETTLE FALLS TAP AND COOKE MOUTAIN TAP | KETTLE FALLS: AVISTA CORP 115KV FEEDER 1, COOKE MOUNTAIN: FERRY CO PUD 115KV FEEDER 1, REPUBLIC: FERRY CO PUD 34.5KV FEEDER 1, REPUBLIC: 115/34.5KV TRANSFORMER 1, REPUBLIC: 115/34.5KV TRANSFORMER 2, COLVILLE-KETTLE FALLS SECTION OF COLVILLE-REPUBLIC NO 1 115KV LINE, KETTLE FALLS-REPUBLIC SECTION OF COLVILLE-REPUBLIC NO 1 115KV LINE
25-05720 | 17484768 | 05/21/2025 07:30 | 05/21/2025 11:30 | RAVER: 500KV CAP GROUP 1 SECTIONS 1,2,3 INCLUDING PCBs 4917, 4919, 4722 AND 500KV REACTIVE BUS | RAVER: PCB 4914, RAVER: PCB 4917, RAVER: PCB 4919, RAVER: PCB 4722, RAVER: PCB 4921, RAVER: 500KV CAP GROUP 1 SECTION 1, RAVER: 500KV CAP GROUP 1 SECTION 2, RAVER: 500KV CAP GROUP 1 SECTION 3 | NOEL, RP, SOC, IROL, WOCN
24-02180 | 15526967 | 05/21/2025 08:00 | 05/21/2025 14:30 | KEELER: PCB A-859 INCLUDING 230KV REACTIVE GROUP 2 CAP SECTION 3 | KEELER: PCB A-859, KEELER: 230KV REACTIVE GROUP 2 CAP SECTION 3 | SOA, NOPE, WOCS
25-02840 | 17221327 | 05/21/2025 08:00 | 05/21/2025 15:00 | MAPLE VALLEY: 230KV CAP GROUP 1 SECT 1, 2, 3, 4 INCL LBDs A-1101, A-1102, A-1103, & A-1104 | MAPLE VALLEY: LBD A-1101, MAPLE VALLEY: LBD A-1102, MAPLE VALLEY: LBD A-1103, MAPLE VALLEY: LBD A-1104, MAPLE VALLEY: PCB A-1146, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 1, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 2, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 3, MAPLE VALLEY: 230KV CAP GROUP 1 SECTION 4 | NOEL, SOC, WOCN, NI
25-05722 | 17484797 | 05/21/2025 12:30 | 05/21/2025 14:30 | ECHO LAKE: 500kV CAP GROUP 1 INCLUDING PCB 5125 | ECHO LAKE: PCB 5125 | BCHT, BCHW, NOEL, SOC, WOCN, NI
25-05724 | 17484992 | 05/21/2025 14:30 | 05/21/2025 16:30 | ECHO LAKE: 500KV CAP GROUP 2 INCLUDING PCB 5127 | ECHO LAKE: PCB 5127, ECHO LAKE: 500KV CAP GROUP 2 | BCHT, NOEL, SOC, WOCN, NI, BCHW, IROL
25-03902 | 17304188 | 05/22/2025 08:00 | 06/02/2025 16:00 | REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | SIG, COR, NWACI
25-01384 | 17175576 | 05/22/2025 08:00 | 05/22/2025 15:00 | SCHULTZ: PCB 5176 |  | WOCN, NOEL
25-02813 | 17221449 | 05/22/2025 08:00 | 05/22/2025 12:00 | RAVER: 500KV CAP GROUP 1 SECTIONS 1, 2, 3 INCLUDING PCB's 4917, 4919, 4722 AND CAP GROUP 1 REACTIVE BUS | RAVER: PCB 4917, RAVER: PCB 4919, RAVER: PCB 4722, RAVER: 500KV CAP GROUP 1 SECTION 1, RAVER: 500KV CAP GROUP 1 SECTION 2, RAVER: 500KV CAP GROUP 1 SECTION 3, RAVER: CAP GROUP 1 REACTIVE BUS | NOEL, RP, SOC, IROL, WOCN
25-00684 | 16834926 | 05/22/2025 08:00 | 05/22/2025 14:00 | GRIZZLY-MALIN PGE NO 2 500KV LINE INCLUDING; MALIN: PCB'S 4070, 4072; GRIZZLY: PCB'S 4046, 4048 | GRIZZLY-MALIN PGE NO 2 500KV LINE, MALIN: PCB 4070, MALIN: PCB 4072, GRIZZLY: PCB 4046, GRIZZLY: PCB 4048, MALIN: PCB 4037, MALIN: 500KV REACTOR 2 | BCHT, BCHW, NI, NWACI, SIG, COI, WOJD
25-01370 |  | 05/26/2025 08:00 | 06/13/2025 15:00 | -PGE- SHERWOOD: 230KV BUS V63 |  | SOA, NOPE, LOAD
25-00847 | 16929397 | 05/26/2025 08:00 | 05/30/2025 15:00 | ALVEY: PCB 5084 |  | NWACI, EWEB
25-03129 | 17264350 | 05/27/2025 07:00 | 05/27/2025 14:00 | TARGHEE-DRUMMOND NO 1 115KV LINE INCLUDING DRUMMOND: PCB B-1681 AND THE 115KV AUX BUS | TARGHEE-DRUMMOND NO 1 115KV LINE, DRUMMOND: PCB B-1681, DRUMMOND: 115KV AUX BUS | SEIL, GEN
25-04313 | 17337935 | 05/27/2025 07:00 | 05/27/2025 10:00 | SNOHOMISH: 115KV CAP GROUP 2 SECTIONS 1, 2 AND 3, INCLUDING PCBS B-907, B-908, B-909 AND B-632 | SNOHOMISH: 115KV CAP GROUP 2 SECTION 2, SNOHOMISH: 115KV CAP GROUP 2 SECTION 3, SNOHOMISH: PCB B-632, SNOHOMISH: 115KV CAP GROUP 2 SECTION 1, SNOHOMISH: PCB B-908, SNOHOMISH: PCB B-907, SNOHOMISH: PCB B-909 | NOEL, SOC, WOCN
25-00868 | 16835586 | 05/27/2025 07:00 | 05/28/2025 15:00 | PAUL: PCB 4542 |  | GEN, WOCS, SOA, NOPE
25-00900 | 16840371 | 05/27/2025 07:30 | 05/27/2025 07:45 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-05450 | 17455950 | 05/27/2025 07:30 | 05/27/2025 12:00 | LONGVIEW: 230KV NORTH AUX BUS | LONGVIEW: PCB A-1378
25-04341 | 17338980 | 05/27/2025 08:00 | 05/29/2025 15:00 | SPRING CREEK-MABTON SECTION OF SPRING CREEK-WINE COUNTRY NO 1 230KV LINE |  | GEN, NWACI, PDCI, WOJD
25-01153 | 16976623 | 05/27/2025 08:00 | 05/30/2025 16:00 | GRAND COULEE-HANFORD NO 1 500KV LINE |  | BCHT, BCHW, GEN, NI, NOH, SIG, WOCN
25-01378 | 17299613 | 05/27/2025 08:00 | 05/29/2025 16:30 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5163 | SCHULTZ: PCB 5163, SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 | WOCN, NOEL, IROL, SOC, SIG
25-02092 | 17133685 | 05/27/2025 08:00 | 06/02/2025 15:00 | CHEHALIS-OLYMPIA NO 1 230KV LINE | CHEHALIS: PCB A-228, OLYMPIA: PCB A-220 | RP, LOAD, SI, NOEL, SOC, WOCN
25-04585 | 17373147 | 05/27/2025 08:00 | 05/27/2025 15:00 | FAIRMOUNT: PCB A-1627 |  | RP
25-05396 |  | 05/27/2025 08:00 | 05/30/2025 18:00 | SCL - SHORELINE-NORTH 120KV LINE INCLUDING NORTH: 120KV BUS 6 AND PSB'S 120-79 & -80 |  | SOC/NOEL
25-04374 | 17339068 | 05/27/2025 08:00 | 05/29/2025 15:00 | WINE COUNTRY: PCB A-1741 |  | WOJD, NOH
25-01661 | 17338664 | 05/27/2025 08:00 | 05/30/2025 16:00 | ALVEY: 115KV SOUTH MAIN BUS INCLUDING PCBs: B-584, B-582, B-580, B-578, B-576, B-574, B-572, B-570, AND FUTURE 115KV MAIN BUS SECTIONALIZING PCB B-581 | ALVEY: SPRNGFLD UTIL BRD 115KV FEEDER 1 TO SPRINGFIELD, MT. VERNON-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 2 115KV LINE, ALVEY: 115/34.5KV TRANSFORMER 1, ALVEY: LANE ELEC COOP 34.5KV FEEDER 1, DILLARD-ALVEY SECTION OF EUGENE-ALVEY NO 2 115KV LINE, HIDEAWAY-ALVEY SECTION OF HAWKINS-ALVEY NO 1 115KV LINE, ALVEY: 230/115KV TRANSFORMER 3, ALVEY: 115KV SOUTH MAIN BUS, ALVEY: 115KV CAP GROUP 1 SECTION 2, ALVEY: 115KV CAP GROUP 1 SECTION 1 | GEN, SCORC
25-01348 | 17049752 | 05/27/2025 08:00 | 05/28/2025 15:00 | MONROE: 500KV CAP GROUP 2, INCLUDING PCB 4715 | MONROE: PCB 4715 | IROL, NI, NOEL, SOC, WOCN
25-03278 | 17261798 | 05/27/2025 08:00 | 05/27/2025 18:30 | JOHN DAY-GRIZZLY 2 500KV LINE INCLUDING BAKEOVEN: 500KV SERIES CAP GROUP 2 AND PCB 5367 | BAKEOVEN: JOHN DAY-GRIZZLY 2 500KV LINE SERIES CAP GROUP 2, JOHN DAY-GRIZZLY NO 2 500KV LINE, .. | NWACI, WOJD, PDCI, BCHT, BCHW, NI, SIG, GRZN
25-00060 | 15162283 | 05/27/2025 08:00 | 05/30/2025 16:30 | PONDEROSA-CORRAL NO 1 230KV LINE INCLUDING PCB'S A-1812 AND A-1815 | PONDEROSA-CORRAL NO 1 230KV LINE INCLUDING PCB'S A-1812 AND A-1815, PONDEROSA-CORRAL NO 1 230KV LINE, PONDEROSA: PCB A-1812, PONDEROSA: PCB A-1815 | COR, GRZN, NWACI
25-05345 | 17482723 | 05/27/2025 08:00 | 05/29/2025 15:00 | ADDY: 230/115KV TRANSFORMER 3 INCLUDING PCB A-171, PCB A-147, 230KV CAP GROUP 1, LBD A-145, 230KV NORTH MAIN BUS, AND 230KV SOUTH MAIN BUS | ADDY: LBD A-145, ADDY: PCB A-171, ADDY: 230/115KV TRANSFORMER 3, ADDY: 230KV NORTH MAIN BUS, ADDY: 230KV SOUTH MAIN BUS, ADDY TAP TO BELL-BOUNDARY NO 3 230KV LINE, ADDY: 230KV CAP GROUP 1, ADDY: PCB A-147, ADDY-CUSICK NO 1 230KV LINE | SOB, WOH
25-04556 |  | 05/27/2025 10:00 | 05/27/2025 12:00 | MURRAY: 115KV CAP GRP 1 SECTIONS 1 AND 2 | MURRAY: 115KV CAP GROUP 1 SECTION 1, MURRAY: 115KV CAP GROUP 1 SECTION 2, MURRAY: PCB B-1745
25-04314 | 17337913 | 05/27/2025 10:00 | 05/27/2025 15:00 | SNOHOMISH: 230KV CAP GROUP 3 SECTIONS 1 AND 2 INCLUDING PCB A-195, LBD-A179 AND PCB A-1040 | SNOHOMISH: 230KV CAP GROUP 3 SECTION 1, SNOHOMISH: 230KV CAP GROUP 3 SECTION 2, SNOHOMISH: PCB A-195, SNOHOMISH: LBD A-179, SNOHOMISH: PCB A-1040 | NOEL, SOC, WOCN
25-00901 | 16840377 | 05/27/2025 11:15 | 05/27/2025 11:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-04294 | 17360564 | 05/27/2025 15:05 | 05/27/2025 19:00 | ALLSTON-CLATSOP NO 1 230KV LINE INCLUDING DRISCOLL TAP AND CLATSOP A-1256 MOD | CLATSOP: PACIFICORP (PACW) 115KV FEEDER 1, CLATSOP: 230/115KV TRANSFORMER 1, ALLSTON-CLATSOP NO 1 230KV LINE | LOAD, SOA, NOPE
25-04751 | 17375004 | 05/28/2025 06:00 | 05/29/2025 16:00 | ALVEY: A-656 TERMNAL OF ALVEY-DIXONVILLE NO 1 230KV LINE | ALVEY-DIXONVILLE NO 1 230KV LINE | EWEB, NWACI
25-04939 | 17401080 | 05/28/2025 07:00 | 05/29/2025 14:00 | FLATHEAD: PCB A-217 |  | MT-NW, FLAT
25-05443 | 17456192 | 05/28/2025 07:30 | 05/28/2025 17:00 | LONGVIEW: 230KV NORTH MAIN BUS INCLUDING PCB'S A-1374, A-1378, AND A-1380 | LONGVIEW: 230KV NORTH MAIN BUS, LEXINGTON-LONGVIEW NO 2 230KV LINE | SOA, LOAD, NOPE
25-04584 | 17373246 | 05/28/2025 08:00 | 05/28/2025 15:00 | FAIRMOUNT: 115KV CAP GROUP 1 SECTION 4 INCLUDING PCB B-1385 | FAIRMOUNT: 115KV CAP GROUP 1 SECTION 4, FAIRMOUNT: PCB B-1385
25-00786 | 17108851 | 05/28/2025 08:00 | 05/29/2025 16:00 | SWAN VALLEY: 115KV MAIN BUS INCLUDING PCBs B-1688, B-1676, B-1665, B-1675, B-1677 AND THE 115KV MAIN BUS PTs | SWAN VALLEY: 115KV MAIN BUS, PALISADES-SWAN VALLEY NO 1 115KV LINE, SWAN VALLEY-TETON NO 1 115KV LINE, SWAN VALLEY-TETON NO 2 115KV LINE, SWAN VALLEY-GOSHEN NO 1 161KV LINE, SWAN VALLEY: 161/115KV TRANSFORMER 3, SWAN VALLEY: LOWER VALLEY ENG 12.5KV FEEDER 1 | GEN, LOAD, SEIL
25-00205 | 17095338 | 05/28/2025 08:00 | 07/28/2025 15:00 | KNAPPA-FERN HILL SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE |  | SOA
25-03623 | 17293890 | 05/28/2025 08:00 | 05/29/2025 17:00 | BROADVIEW-GARRISON NO 1 500KV LINE | GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, GEN
25-03627 | 17293998 | 05/28/2025 08:00 | 05/29/2025 17:00 | BROADVIEW-GARRISON NO 2 500KV LINE | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 | MT-NW, GEN
25-02225 |  | 05/28/2025 08:00 | 05/28/2025 16:30 | E. E. CLOUSE-GOLDENDALE SECTION OF CHENOWETH-GOLDENDALE NO 1 115KV LINE
25-05843 |  | 05/29/2025 07:00 | 05/29/2025 15:00 | OLYMPIA: 230/115KV TRANSFORMER 2
25-05452 | 17456279 | 05/29/2025 07:30 | 05/29/2025 12:00 | LONGVIEW: 230KV NORTH AUX BUS | LONGVIEW: PCB A-1378
25-02445 | 17287739 | 05/29/2025 08:00 | 05/29/2025 15:00 | PONDEROSA: PCB A-1812
25-02222 | 17182100 | 05/29/2025 10:00 | 06/30/2025 15:00 | NOTI CREEK TAP: B-971 AND B-972 TERMINALS OF NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | FERN RIDGE-NOTI CREEK SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK-WALTON SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | LOAD, SCORC
25-03028 | 17246735 | 05/29/2025 11:30 | 05/29/2025 13:00 | CAL YOUNG: PCB 4870 | CAL YOUNG-WILLAKENZIE 115KV LINE | EWEB
25-04336 | 17338652 | 05/30/2025 08:00 | 05/30/2025 14:30 | GRAND COULEE: PCB 7182, GRAND COULEE: PCB 7382 |  | GEN, NOH, WOCN
25-03094 | 17406178 | 05/30/2025 08:00 | 05/30/2025 15:00 | RUPPERT ROAD TAP TO RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | RED MOUNTAIN-RUPPERT ROAD SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, RUPPERT ROAD: BENTON REA 115KV FEEDER 1 | TCLA